## 📋 Cover
ResolvX — Risk Register
GRC Compliance & Audit Readiness Program ¦ Phase 2: Risk & Controls
Methodology: NIST SP 800-30 Rev.1 ¦ ISO 27001:2022 ¦ FAIR
Document Information
Version | 1.1
Status | Active
Classification | Internal — Confidential
Program Owner | Derick G. Dmello : GRC Lead
Review Cycle | Quarterly
Last Updated | 2026-07-31
Risk Count | 25 Risks ¦ 5 Categories
Governing Standard | NIST SP 800-30 Rev. 1 ¦ ISO 27001:2022 ¦ FAIR
Risk Level Legend
🔴 CRITICAL | Score 20–25 ¦ Immediate escalation to CISO. Treatment within 72 hours.
🔴 HIGH | Score 12–19 ¦ Escalate to GRC Lead. Treatment plan within 30 days.
🟠 MODERATE | Score 7–11 ¦ Assign to control owner. Treatment within 90 days.
🟡 LOW | Score 4–6 ¦ Monitor quarterly. Accept or treat at discretion.
🟢 VERY LOW | Score 1–3 ¦ Accept. Document rationale. Review annually.
Sheets in This Workbook
📋 Cover | This page — document info, legend, and navigation
📊 Risk Register | Full 25-risk register with scoring, controls, and treatment
🗺️ Heat Map | Visual 5×5 risk heat map showing inherent vs residual positions
📈 Summary | Category breakdown, risk level distribution, FAIR ALE totals

## 📊 Risk Register
ResolvX — Risk Register v1.0 ¦ GRC Compliance & Audit Readiness Program ¦ NIST SP 800-30 ¦ ISO 27001:2022 ¦ FAIR
Risk ID | Category | Risk Description | Threat Source | Affected Assets | Inh. L (1-5) | Inh. I (1-5) | Inh. Score | Inh. Level | Current Controls | Control Effectiveness | Res. L (1-5) | Res. I (1-5) | Res. Score | Res. Level | FAIR ALE ($) | Treatment | Treatment Actions | Control Owner | Target Date | Status | ISO 27001 Ref | SOC 2 TSC Ref
RSK-001 | Cyber Threat | Ransomware attack encrypts production systems, causing platform outage and data unavailability | External — Organised cybercriminal group (RaaS) | Production VPC, RDS Database, S3 Object Storage | 5 | 5 | 25 | CRITICAL | EDR on endpoints, AWS GuardDuty, network segmentation, daily RDS snapshots; Immutable Critical-tier backup copy defined (POL-009 §6.4); CloudTrail S3 MFA-delete (POL-007 §6) | Strong | 2 | 4 | 8 | MODERATE | $350,000 – $1,200,000 | Mitigate | Deploy immutable S3 backups; implement AWS Backup with vault lock; enforce MFA-delete on S3; conduct tabletop ransomware simulation [Updated 2026-07-31] Immutable backup and MFA-delete now formalised; ransomware tabletop (IR-TTX-001) already exercised. Remaining: AWS Backup vault lock, active-passive DR site. | Head of Cloud Ops | 2026-Q2 | In Progress | A.8 (Operations Security) | CC7.1, CC7.2, A1.2
RSK-002 | Cyber Threat | Phishing campaign compromises employee credentials, enabling unauthorised access to internal systems and client data | External — Threat actor / Business Email Compromise group | M365 Email, Okta SSO, Corporate Laptops, GitHub | 5 | 4 | 20 | CRITICAL | Okta MFA enforced, phishing-resistant email filtering, security awareness training (annual); FIDO2 hardware key requirement for privileged users (POL-003 §5.1); Okta ThreatInsight (POL-012 §4) | Strong | 2 | 3 | 6 | LOW | $95,000 – $420,000 | Mitigate | Implement phishing-resistant MFA (FIDO2/passkeys); increase security awareness training to quarterly; deploy email sandboxing; enable Okta ThreatInsight [Updated 2026-07-31] FIDO2 and ThreatInsight now formalised in policy. Remaining: quarterly phishing simulation cadence, email sandboxing. | IT Administrator | 2026-Q2 | In Progress | A.6 (Human Resource Security) | CC1.4, CC6.1, CC6.2
RSK-003 | Cyber Threat | Exploitation of unpatched vulnerability in public-facing API gateway leads to unauthorised data exfiltration | External — Opportunistic attacker / APT group | API Gateway, Production Application, RDS Database | 4 | 5 | 20 | CRITICAL | WAF (AWS WAF), quarterly vulnerability scans, bug bounty program; 30-day High-severity patch SLA, continuous Snyk scanning, automatic ticketing (POL-010) | Strong | 2 | 4 | 8 | MODERATE | $280,000 – $950,000 | Mitigate | Implement continuous vulnerability scanning (weekly); establish 30-day patching SLA for critical CVEs; conduct annual penetration test; enable AWS Shield Advanced [Updated 2026-07-31] Patch SLA and continuous scanning now formalised. Remaining: named annual pentest cadence, AWS Shield Advanced. | DevSecOps Engineer | 2026-Q1 | In Progress | A.8 (Vulnerability Management) | CC7.1, CC8.1
RSK-004 | Cyber Threat | Insider threat — malicious or negligent employee exfiltrates sensitive client dispute data | Internal — Malicious or negligent employee/contractor | RDS Database, S3 Storage, M365 SharePoint, Dispute Case Files | 3 | 5 | 15 | HIGH | Role-based access control, AWS CloudTrail audit logging, offboarding checklist; DLP scope and roadmap (POL-019); quarterly access reviews (POL-003 §8); SIEM roadmap (POL-007 §8) | Strong | 2 | 3 | 6 | LOW | $150,000 – $600,000 | Mitigate | Implement Data Loss Prevention (DLP) tooling; enforce least-privilege access reviews quarterly; deploy UEBA alerting via SIEM; strengthen contractor access controls [Updated 2026-07-31] DLP policy formalised with documented residual risk acceptance for remaining coverage gaps (API/S3/endpoint). | GRC Lead | 2026-Q3 | In Progress | A.5, A.6 (Access Control, HR Security) | CC6.2, CC6.3, CC9.2
RSK-005 | Cyber Threat | Supply chain attack via compromised third-party software dependency introduces malicious code into ResolvX platform | External — Nation-state or sophisticated threat actor targeting software supply chain | GitHub CI/CD Pipeline, Production Application, Customer Data | 3 | 5 | 15 | HIGH | GitHub dependency scanning (Dependabot), code review process, signed commits; SCA/SAST/container scanning in CI/CD (POL-018 §3, §6.1); production dependency standards (POL-011 §6) | Moderate | 2 | 4 | 8 | MODERATE | $200,000 – $800,000 | Mitigate | Implement SBOM (Software Bill of Materials) generation; enforce code signing for all deployments; integrate SAST/SCA into CI/CD pipeline; establish third-party software vetting process [Updated 2026-07-31] Dependency scanning now formalised. Remaining: SBOM generation, code signing. | DevSecOps Engineer | 2026-Q2 | In Progress | A.8 (Secure Development) | CC8.1, CC9.1
RSK-006 | Cloud & Infrastructure | AWS S3 bucket misconfiguration exposes sensitive client PII and financial data to public internet | Internal — Configuration error / human mistake | S3 Object Storage, Client Dispute Files, PII Data | 4 | 5 | 20 | CRITICAL | AWS Config rules, S3 Block Public Access enforced at account level; CIS AWS Foundations Benchmark baseline; public S3 disabled by default (POL-022 §6) | Strong | 2 | 4 | 8 | MODERATE | $180,000 – $750,000 | Mitigate | Enable AWS Security Hub with CIS benchmark checks; implement Infrastructure-as-Code (Terraform) with policy guardrails; conduct monthly cloud security posture reviews; implement S3 Object Lock [Updated 2026-07-31] Cloud hardening baseline now formalised. Remaining: named Security Hub deployment, S3 Object Lock. | Head of Cloud Ops | 2026-Q1 | In Progress | A.8 (Asset Management, Operations) | CC6.1, CC7.1, CC7.2
RSK-007 | Cloud & Infrastructure | Production AWS environment outage due to regional failure causes extended platform unavailability, breaching client SLAs | Environmental — AWS infrastructure failure / natural disaster | Production VPC (us-east-1), EKS Cluster, RDS Database | 3 | 4 | 12 | HIGH | Multi-AZ RDS deployment, EKS across 3 availability zones, Route 53 health checks; RTO/RPO targets defined and tested (POL-008); backup restoration regime (POL-009); DR Failover Tabletop Test Report evidences a successful exercise | Strong | 1 | 3 | 3 | VERY LOW | N/A | Mitigate | Implement active-passive DR in us-west-2; define and test RTO/RPO targets quarterly; establish runbook for regional failover; document and test BCP procedures [Updated 2026-07-31] BCP/DR formally tested for the first time (Operation Steady Ground, 2026-07-30) — 98% of RTO budget used, data integrity confirmed. Remaining: dedicated us-west-2 active-passive site. | VP Engineering | 2026-Q3 | In Progress | A.5 (Business Continuity) | A1.1, A1.2, A1.3
RSK-008 | Cloud & Infrastructure | Overprivileged IAM roles allow lateral movement across AWS environments following an initial compromise | Internal/External — Exploited by attacker following initial access | AWS IAM, Production VPC, All AWS Services | 4 | 4 | 16 | HIGH | IAM roles in use, root account MFA enabled, basic least-privilege policy; IAM least-privilege baseline (POL-022 §6); high-blast-radius IAM changes gated (POL-013 §3) | Moderate | 2 | 4 | 8 | MODERATE | $130,000 – $520,000 | Mitigate | Conduct full IAM access review and implement least-privilege; enable AWS IAM Access Analyzer; deploy AWS SCPs (Service Control Policies); implement privileged access workstations for cloud admins [Updated 2026-07-31] Least-privilege standard and change gating now formalised. Remaining: named IAM Access Analyzer, SCPs. | Head of Cloud Ops | 2026-Q2 | In Progress | A.8 (Access Control) | CC6.1, CC6.2, CC6.3
RSK-009 | Cloud & Infrastructure | Inadequate secrets management exposes API keys and database credentials via source code or environment variables | Internal — Developer error / insecure coding practice | GitHub Repositories, CI/CD Pipeline, Production Database | 4 | 4 | 16 | HIGH | AWS Secrets Manager in use for some credentials, .gitignore policies; 1Password/Secrets Manager mandate (POL-012 §3); Snyk secret scanning with automatic ticketing (POL-010 §6.1); cryptographic key lifecycle (POL-021 §4) | Strong | 1 | 3 | 3 | VERY LOW | N/A | Mitigate | Mandate AWS Secrets Manager for ALL credentials; implement GitHub secret scanning with push protection; conduct codebase audit for hardcoded secrets; enforce pre-commit hooks [Updated 2026-07-31] Fully formalised across POL-012, POL-010, and POL-021 — secret storage, scanning, and key lifecycle all governed. | DevSecOps Engineer | Delivered 2026-07-31 | Mitigated | A.8 (Cryptography, Operations) | CC6.7, CC8.1
RSK-010 | Cloud & Infrastructure | Insufficient logging and monitoring coverage creates blind spots, delaying detection of security incidents | Internal — Process gap / resource constraint | CloudWatch, CloudTrail, EKS, RDS, Application Layer | 3 | 3 | 9 | MODERATE | CloudTrail enabled at account level, basic CloudWatch alarms for infra metrics; Full logging and monitoring programme (POL-007) — log sources, retention, SIEM roadmap, correlation rules | Strong | 1 | 3 | 3 | VERY LOW | N/A | Mitigate | Implement centralised SIEM with log aggregation from all AWS sources; define and implement alert rules for NIST IR indicators; establish 24hr log retention baseline with 12-month archive [Updated 2026-07-31] This was the exact gap POL-007 was built to close. Interim weekly Secondary review compensates until SIEM Stage 2. | Head of Cloud Ops | Delivered 2026-07-31 | Mitigated | A.8 (Logging and Monitoring) | CC7.1, CC7.2, CC4.2
RSK-011 | Vendor & Third-Party | AWS service disruption or contractual change materially impacts ResolvX platform availability and operations | External — Vendor / CSP operational or commercial risk | Entire ResolvX Platform (100% AWS-hosted) | 3 | 5 | 15 | HIGH | AWS Enterprise Support contract, multi-AZ deployment, AWS status monitoring | Moderate | 2 | 4 | 8 | MODERATE | N/A | Transfer / Mitigate | Document AWS shared responsibility matrix; evaluate multi-cloud DR strategy; maintain current AWS SLA documentation; include cloud concentration risk in annual risk review | VP Engineering | 2026-Q4 | Open | A.5 (Supplier Relationships) | CC9.1, CC9.2
RSK-012 | Vendor & Third-Party | Stripe payment processing integration breach exposes cardholder data and triggers PCI-DSS regulatory action | External — Stripe incident / integration vulnerability | Payment Processing API, Cardholder Data Environment | 3 | 5 | 15 | HIGH | Stripe handles card data directly (tokenisation), PCI-DSS SAQ A compliance path | Moderate | 2 | 4 | 8 | MODERATE | $250,000 – $850,000 | Mitigate | Obtain and review Stripe annual PCI-DSS AOC; ensure scope reduction via Stripe.js tokenisation; document CDE scoping in PCI-DSS SAQ; conduct annual PCI gap assessment | GRC Lead | 2026-Q2 | Open | A.5 (Supplier Relationships) | CC9.1, CC9.2
RSK-013 | Vendor & Third-Party | Okta identity platform outage or breach disables authentication for all ResolvX employees and client-facing services | External — Vendor incident (as experienced in 2022/2023 Okta breaches) | Okta SSO, All Internal Systems, Client Portal Authentication | 3 | 4 | 12 | HIGH | Okta MFA enforced, break-glass accounts documented; Break-glass credential handling with dual control and post-use rotation (POL-012 §5) | Strong | 1 | 3 | 3 | VERY LOW | N/A | Mitigate | Document and test break-glass emergency access procedure; review Okta SOC 2 Type II report annually; implement Okta's recommended security hardening baseline; evaluate backup authentication path [Updated 2026-07-31] Break-glass process now fully documented and testable via the same mechanism as any other credential exception. | IT Administrator | Delivered 2026-07-31 | Mitigated | A.5 (Supplier Relationships) | CC6.1, CC9.1
RSK-014 | Vendor & Third-Party | Third-party vendor with access to ResolvX data has inadequate security controls, creating a data breach vector | External — Weak vendor security posture | PII Data, Client Dispute Records, Integration APIs | 3 | 4 | 12 | HIGH | Basic vendor contracts in place, no formal vendor security assessment programme; Formal TPRM programme (POL-005) with tiered Vendor Security Questionnaire (Appendix A) | Strong | 1 | 3 | 3 | VERY LOW | N/A | Mitigate | Implement formal vendor risk assessment programme (TPRM); require SOC 2 or equivalent from all Tier 1 vendors; include security requirements in all vendor contracts; conduct annual vendor reviews [Updated 2026-07-31] TPRM programme and now a fillable VSQ appendix are in place — vendor assessment is a real, evidenced process. | GRC Lead | Delivered 2026-07-31 | Mitigated | A.5 (Supplier Relationships) | CC9.1, CC9.2
RSK-015 | Vendor & Third-Party | SendGrid (Twilio) email platform misuse or misconfiguration enables phishing impersonation of ResolvX communications | External/Internal — Misconfiguration or vendor compromise | Transactional Email Infrastructure, Client PII (Email Addresses) | 3 | 3 | 9 | MODERATE | SendGrid account MFA enabled, basic domain authentication | Moderate | 2 | 2 | 4 | LOW | N/A | Mitigate | Implement DMARC (reject policy), DKIM, and SPF for all ResolvX sending domains; configure SendGrid IP allowlisting; review SendGrid access quarterly; monitor for domain spoofing | IT Administrator | 2026-Q1 | In Progress | A.8 (Communications Security) | CC6.6, CC6.7
RSK-016 | Compliance & Regulatory | Failure to achieve SOC 2 Type II certification results in loss of enterprise client contracts and pipeline opportunities | Internal — Program execution risk / resource constraint | Entire GRC Program, Commercial Pipeline, Client Contracts | 3 | 5 | 15 | HIGH | GRC program initiated, roadmap defined, Phase 1 complete; Full 26-policy suite delivered across all Trust Services Criteria domains, plus evidence artifacts (Monitoring Report, DR Test Report, Exception Register) | Strong | 2 | 3 | 6 | LOW | $500,000+ in ARR pipeline risk | Mitigate | Execute GRC program roadmap on schedule; engage SOC 2 auditor by Q3 2026; ensure all TSC controls implemented and evidenced; conduct pre-audit readiness assessment [Updated 2026-07-31] The GRC roadmap referenced in this risk's treatment action is now substantively executed. Remaining: engage external auditor and complete the SOC 2 Type II observation window itself. | GRC Lead | 2026-Q3 | In Progress | A.5 (Compliance) | CC4.1, CC4.2
RSK-017 | Compliance & Regulatory | GDPR violation due to improper handling of EU client personal data results in regulatory investigation and fine | Internal/External — Process gap, data subject request failure, or breach | EU Client Data, Dispute Records, M365, RDS Database | 3 | 5 | 15 | HIGH | Privacy policy published, DPA clauses in client contracts, legal counsel engaged; ROPA/DSR process (POL-006); formal breach risk methodology and US/EU notification framework (POL-016) | Strong | 1 | 3 | 3 | VERY LOW | $200,000 – $2,000,000 (up to 4% global revenue) | Mitigate | Conduct GDPR data mapping and Records of Processing Activities (ROPA); implement Data Subject Request (DSR) process; appoint Data Protection Lead; review DPAs with all EU data processors [Updated 2026-07-31] POL-016 adds the risk-determination methodology and sign-off authority that POL-006 alone didn't define. | General Counsel | Delivered 2026-07-31 | Mitigated | A.5 (Privacy, Compliance) | P1, P2, P3, P4, P5
RSK-018 | Compliance & Regulatory | PCI-DSS non-compliance due to inadequate cardholder data environment controls results in card brand fines and potential loss of payment processing capability | Internal — Control gap / scope misunderstanding | Cardholder Data Environment, Stripe Integration, Production Systems | 3 | 4 | 12 | HIGH | Stripe tokenisation reduces CDE scope, SAQ A path identified | Moderate | 2 | 3 | 6 | LOW | N/A | Mitigate | Complete PCI-DSS SAQ A or SAQ A-EP based on scoping assessment; document network segmentation; conduct quarterly ASV scans; implement annual PCI compliance review process | GRC Lead | 2026-Q2 | Open | A.8 (Compliance) | CC4.1, CC4.2
RSK-019 | Compliance & Regulatory | CCPA non-compliance due to failure to honour California consumer data rights requests (access, deletion, opt-out) results in regulatory action | Internal — Process gap / absence of consumer rights workflow | California Consumer PII, RDS Database, CRM Systems | 3 | 3 | 9 | MODERATE | Privacy policy references CCPA rights, legal counsel aware | Weak | 2 | 3 | 6 | LOW | N/A | Mitigate | Implement documented CCPA consumer rights request process with 45-day response SLA; conduct data inventory to identify all California consumer PII; train Customer Success on DSR handling | General Counsel | 2026-Q3 | Open | A.5 (Privacy, Compliance) | P1, P2, P4, P8
RSK-020 | Compliance & Regulatory | Contractual SLA breach due to platform downtime exceeds client-agreed availability thresholds, triggering financial penalties | Internal/External — Platform failure or cloud outage | Production Platform, Client Contracts, Financial Operations | 3 | 3 | 9 | MODERATE | Multi-AZ deployment, Route 53 health checks, basic uptime monitoring | Moderate | 2 | 2 | 4 | LOW | N/A | Accept / Mitigate | Define internal SLA targets above contracted client SLAs (buffer zones); implement real-time availability dashboard; document SLA credit calculation process; review SLA terms in next contract cycle | VP Engineering | 2026-Q4 | Open | A.5 (Business Continuity, Compliance) | A1.1, A1.3, CC4.2
RSK-021 | Human & Operational | Inadequate security awareness training results in employees failing to recognise social engineering attacks | Internal — Human error / lack of security culture | All Employees, Corporate IT, Client Data | 4 | 3 | 12 | HIGH | Annual security awareness training, phishing simulation (ad hoc); Mandatory onboarding + annual security awareness training with escalation (POL-023 §5) | Moderate | 2 | 2 | 4 | LOW | N/A | Mitigate | Implement quarterly phishing simulations with targeted training for failures; migrate to role-based security training programme; track completion rates and report to CISO monthly [Updated 2026-07-31] Training mandate and escalation path now formalised. Remaining: quarterly phishing simulation cadence. | Head of HR | 2026-Q2 | In Progress | A.6 (Human Resource Security) | CC1.4, CC2.2
RSK-022 | Human & Operational | Inadequate offboarding process leaves access credentials and permissions active for departed employees or contractors | Internal — Process gap / HR-IT coordination failure | Okta SSO, AWS IAM, GitHub, M365, SaaS Tools | 3 | 4 | 12 | HIGH | Offboarding checklist exists, IT notified via email; Same-day access revocation at termination, exceeding the original 24-hour target (POL-023 §8); quarterly dormant-account reconciliation (POL-023 §8.1) | Strong | 1 | 3 | 3 | VERY LOW | N/A | Mitigate | Automate offboarding via Okta lifecycle management (deprovisioning on HR trigger); conduct monthly access certification reviews; implement 24-hour SLA for access revocation on termination [Updated 2026-07-31] Same-day revocation exceeds this risk's original treatment target; dormant-account reconciliation adds a safety net HR notification alone didn't have. | IT Administrator | Delivered 2026-07-31 | Mitigated | A.6 (Human Resource Security) | CC6.2, CC6.3
RSK-023 | Human & Operational | Key person dependency — critical GRC and security knowledge concentrated in one or two individuals creates operational continuity risk | Internal — Organisational / resource risk | GRC Program, Security Operations, Compliance Programme | 3 | 3 | 9 | MODERATE | GRC documentation programme initiated (this repository); This entire 26-policy suite formally documents ResolvX's GRC processes, removing single-person dependency on undocumented practice | Strong | 1 | 2 | 2 | VERY LOW | N/A | Mitigate | Document all GRC processes and procedures (this repository); cross-train secondary owners for all control domains; build internal GRC knowledge base; include succession planning in annual HR review [Updated 2026-07-31] The most directly-addressed risk in the register — every process previously undocumented now has a named, versioned, owned policy. | CISO | Delivered 2026-07-31 | Mitigated | A.6 (Human Resource Security) | CC1.3, CC1.4
RSK-024 | Human & Operational | Change management failure — uncontrolled infrastructure or code change causes production outage or security regression | Internal — Process gap / insufficient change controls | Production VPC, Application Codebase, AWS Configuration | 3 | 4 | 12 | HIGH | GitHub branch protection, basic PR review process, informal change communication; Formal change categories, peer review, and testing gates (POL-013) | Strong | 1 | 2 | 2 | VERY LOW | N/A | Mitigate | Implement formal Change Advisory Board (CAB) process; enforce mandatory security review for high-risk changes; define change categories (standard, normal, emergency) with approval workflows [Updated 2026-07-31] This was the exact gap POL-013 was built to close — CAB-equivalent process, security review dimension, freeze windows. | VP Engineering | Delivered 2026-07-31 | Mitigated | A.8 (Change Management) | CC8.1
RSK-025 | Human & Operational | Absence of a tested Business Continuity Plan means ResolvX cannot effectively respond to a major operational disruption | Internal — Process gap / BCP not formalised or tested | Entire Business Operations, Client-Facing Platform | 3 | 4 | 12 | HIGH | Informal recovery procedures exist, AWS DR architecture partially defined; Formal BCP/DR policy and plan (POL-008), backup regime (POL-009), and a completed, evidenced tabletop exercise (DR Failover Tabletop Test Report) | Strong | 1 | 3 | 3 | VERY LOW | N/A | Mitigate | Develop and document formal BCP aligned to ISO 22301; define RTO/RPO for all critical systems; conduct annual BCP tabletop exercise; integrate BCP with IR plan [Updated 2026-07-31] Fully delivered and tested — the cleanest closure in this register. Recovered within 98% of RTO budget with no critical findings. | VP Engineering | Delivered 2026-07-31 | Mitigated | A.5 (Business Continuity) | A1.1, A1.2, A1.3

## 🗺️ Heat Map
ResolvX — Risk Heat Map ¦ Inherent Risk Position
Each cell shows Risk IDs plotted at their Inherent Likelihood × Impact position
|  | Impact 1 (Very Low) | Impact 2 (Low) | Impact 3 (Moderate) | Impact 4 (High) | Impact 5 (Very High)
| Likelihood 5 (Very High) | Score: 5 — | Score: 10 — | Score: 15 — | Score: 20 RSK-002 | Score: 25 RSK-001
| Likelihood 4 (High) | Score: 4 — | Score: 8 — | Score: 12 RSK-021 | Score: 16 RSK-008 RSK-009 | Score: 20 RSK-003 RSK-006
| Likelihood 3 (Moderate) | Score: 3 — | Score: 6 — | Score: 9 RSK-010 RSK-015 RSK-019 RSK-020 RSK-023 | Score: 12 RSK-007 RSK-013 RSK-014 RSK-018 RSK-022 RSK-024 RSK-025 | Score: 15 RSK-004 RSK-005 RSK-011 RSK-012 RSK-016 RSK-017
| Likelihood 2 (Low) | Score: 2 — | Score: 4 — | Score: 6 — | Score: 8 — | Score: 10 —
| Likelihood 1 (Very Low) | Score: 1 — | Score: 2 — | Score: 3 — | Score: 4 — | Score: 5 —
ResolvX — Risk Heat Map ¦ Residual Risk Position (After Controls)
Residual positions reflect risk after current controls are applied
|  | Impact 1 (Very Low) | Impact 2 (Low) | Impact 3 (Moderate) | Impact 4 (High) | Impact 5 (Very High)
| Likelihood 5 (Very High) | Score: 5 — | Score: 10 — | Score: 15 — | Score: 20 — | Score: 25 —
| Likelihood 4 (High) | Score: 4 — | Score: 8 — | Score: 12 — | Score: 16 — | Score: 20 —
| Likelihood 3 (Moderate) | Score: 3 — | Score: 6 — | Score: 9 — | Score: 12 — | Score: 15 —
| Likelihood 2 (Low) | Score: 2 — | Score: 4 RSK-015 RSK-020 RSK-021 | Score: 6 RSK-002 RSK-004 RSK-016 RSK-018 RSK-019 | Score: 8 RSK-001 RSK-003 RSK-005 RSK-006 RSK-008 RSK-011 RSK-012 | Score: 10 —
| Likelihood 1 (Very Low) | Score: 1 — | Score: 2 RSK-023 RSK-024 | Score: 3 RSK-007 RSK-009 RSK-010 RSK-013 RSK-014 RSK-017 RSK-022 RSK-025 | Score: 4 — | Score: 5 —

## 📈 Summary
ResolvX — Risk Register Summary Dashboard
Risk Count by Category | Total | Critical/High | Moderate | Low/VLow
Cyber Threat | 5 | 0 | 3 | 2
Cloud & Infrastructure | 5 | 0 | 2 | 3
Vendor & Third-Party | 5 | 0 | 2 | 3
Compliance & Regulatory | 5 | 0 | 0 | 5
Human & Operational | 5 | 0 | 0 | 5
Residual Risk Level Distribution | Count | % of Total | Action Required
CRITICAL | 0 | 0% | Immediate escalation — treatment within 72 hours
HIGH | 0 | 0% | Treatment plan required within 30 days
MODERATE | 7 | 28% | Treatment plan within 90 days
LOW | 8 | 32% | Monitor quarterly — accept or treat at discretion
VERY LOW | 10 | 40% | Accept — document rationale, review annually
FAIR ALE Summary — High & Critical Risks
Risk ID | Risk Description | Residual Level | FAIR ALE ($) | Treatment
RSK-001 | Ransomware attack encrypts production systems, causing platf… | MODERATE | $350,000 – $1,200,000 | In Progress
RSK-002 | Phishing campaign compromises employee credentials, enabling… | LOW | $95,000 – $420,000 | In Progress
RSK-003 | Exploitation of unpatched vulnerability in public-facing API… | MODERATE | $280,000 – $950,000 | In Progress
RSK-004 | Insider threat — malicious or negligent employee exfiltrates… | LOW | $150,000 – $600,000 | In Progress
RSK-005 | Supply chain attack via compromised third-party software dep… | MODERATE | $200,000 – $800,000 | In Progress
RSK-006 | AWS S3 bucket misconfiguration exposes sensitive client PII … | MODERATE | $180,000 – $750,000 | In Progress
RSK-008 | Overprivileged IAM roles allow lateral movement across AWS e… | MODERATE | $130,000 – $520,000 | In Progress
RSK-012 | Stripe payment processing integration breach exposes cardhol… | MODERATE | $250,000 – $850,000 | Open
RSK-016 | Failure to achieve SOC 2 Type II certification results in lo… | LOW | $500,000+ in ARR pipeline risk | In Progress
RSK-017 | GDPR violation due to improper handling of EU client persona… | VERY LOW | $200,000 – $2,000,000 (up to 4% global revenue) | Mitigated