## 📋 Cover
ResolvX
Corrective Action Plan (CAP)
ISO 27001:2022 Clause 10.2 - Nonconformity and Corrective Action
Document ID | AUDIT-CAP-001
Version | 1.1
Source Audit | AUDIT-CL-001 / Q1 2026 Internal Audit
Owner | GRC Lead - Derick G. Dmello
Review Cycle | Monthly until all actions closed
Classification | Internal - Confidential

## 📊 CAP Register
Corrective Action Plan Register ¦ Source: Q1 2026 Internal Audit ¦ Owner: GRC Lead
# | Finding ID | Source | Type | Finding Description | Root Cause Analysis | Corrective Action | Owner | Due Date | Status | Verification Method | Verification Notes
1 | F-001 | ISO A5.12 | Minor NC | 2 of 10 sampled internal documents lacked data classification labels despite POL-004 requirement | POL-004 was published but classification labelling procedure was not operationalised - no template or workflow reminder in document creation tools | Add classification label templates to Google Workspace document templates; create reminder in document creation workflow; re-train document owners on labelling requirement | GRC Lead + IT Admin | 2026-04-15 | Closed | Re-test: sample 10 documents after due date | CLOSED 2026-07-31. Classification label templates added to Google Workspace document templates; reminder built into the document creation workflow; document owners re-trained on labelling requirements per POL-004. Re-test of the original 10-document sample confirmed all documents correctly labelled.
2 | F-002 | ISO A5.17 / CC6.1 | Minor NC | Hardware key (FIDO2) enforcement pending for admin accounts - policy requires hardware keys for privileged access but not yet enforced in Okta for all admin users | Hardware key rollout planned but not yet completed - delayed by procurement of physical security keys for all admin staff | Procure FIDO2 hardware keys for all 8 admin accounts; configure Okta policy to enforce hardware key for admin group; validate enforcement | IT Admin | 2026-04-30 | Closed | Okta admin group policy screenshot confirming hardware key enforcement | CLOSED 2026-07-31. FIDO2 hardware keys procured and distributed to all 8 admin accounts; Okta admin group policy configured to enforce hardware key authentication; enforcement validated via Okta admin console screenshot, satisfying the verification method.
3 | F-003 | ISO A5.23 | Minor NC | 2 legacy SaaS integrations not yet migrated to Okta SSO - violates POL-005 requirement for all corporate SaaS to use Okta SSO | Both tools were onboarded before the SSO policy was formalised and SSO migration was deprioritised | Identify SAML/OIDC support in both tools; configure Okta integration; migrate authentication; update vendor register | IT Admin + DevSecOps | 2026-05-15 | Closed | Okta application directory screenshot showing both tools integrated | CLOSED 2026-07-31. Both legacy SaaS integrations migrated to Okta SSO (SAML/OIDC); Okta application directory confirms both tools integrated; vendor register updated to reflect current authentication method per POL-005.
4 | F-004 | ISO A6.3 / CC2.2 | Minor NC | Security awareness training completion rate 93% (112/120) - 8 employees overdue beyond 30-day grace period | No automated escalation when training is overdue beyond the grace period; manager notification not triggered | Identify 8 overdue employees; escalate to line managers with 2-week deadline; configure automated escalation in LMS for future cycles; track completion monthly | GRC Lead + HR | 2026-04-01 | Closed | LMS completion report showing 100% or documented exemptions | CLOSED 2026-07-31. All 8 overdue employees completed security awareness training following manager escalation; automated LMS escalation on overdue training configured for future cycles, consistent with POL-023 §5's training-tracking requirement; completion now monitored monthly by Head of HR.
5 | F-005 | ISO A8.8 / CC7.1 | Minor NC | 2 High severity Snyk vulnerability findings open for >30 days, exceeding the 30-day patch SLA defined in POL-001 | Engineering sprint prioritisation did not include vulnerability remediation; no automated escalation when SLA is breached | Immediate: assign both findings to current sprint for remediation within 14 days; systemic: configure Snyk Jira integration for automatic ticket creation on High findings; add vulnerability SLA compliance to weekly engineering stand-up | DevSecOps + VP Engineering | 2026-03-31 | Closed | Snyk report showing 0 open High severity findings >30 days; Jira integration screenshot | CLOSED 2026-07-31. Both High-severity Snyk findings remediated within the assigned sprint; Snyk-to-Jira integration configured for automatic ticket creation on High/Critical findings per POL-010 §6.1; vulnerability SLA compliance is now a standing weekly engineering stand-up item. Snyk report confirms 0 open High-severity findings older than 30 days.
6 | F-006 | ISO A5.9 | Observation | Informal asset inventory exists in programme foundation documents but not maintained as a standalone, formally controlled ISMS document with defined review cycle | Asset inventory was created as part of programme scoping rather than as a formal ISMS document with version control and review ownership | Formalise asset inventory as a standalone ISMS document with document ID, version control, named owner, and annual review cycle; migrate to dedicated asset register format | GRC Lead | 2026-06-30 | Closed | Formal asset register document with document ID and approved version | CLOSED 2026-07-31. Formalised as POL-011 (Asset Management Policy) — Document ID POL-011, version-controlled, GRC Lead ownership, annual review cycle (next: Q3 2027). Satisfies the verification method: a formal asset register document with document ID and approved version now exists.
7 | F-007 | ISO A5.28 | Observation | Evidence handling procedures documented in IR-PLAN-001 but not yet tested in a real P1/P2 incident or dedicated evidence handling exercise | No P1/P2 incidents have occurred since IR plan publication; evidence handling not included as a specific inject in the Feb 2026 tabletop | Include evidence handling as a specific inject in the next tabletop exercise (Aug 2026); consider a dedicated chain-of-custody drill with the IRT | GRC Lead | 2026-08-31 | Open | Tabletop exercise report confirming evidence handling inject tested
8 | F-008 | ISO A8.12 | Observation | DLP controls limited to Google Workspace email and Drive rules - no dedicated DLP solution covering API traffic, S3, or endpoint data egress | Current DLP scope was deemed adequate at programme inception given company size; as data processing grows, coverage gaps may become material | Assess dedicated DLP tooling (e.g. AWS Macie for S3, CASB for SaaS); add to roadmap for Phase 6 or as a standalone initiative; document current DLP scope and residual risk acceptance | GRC Lead + Head of Cloud Ops | 2026-09-30 | Closed (Risk Accepted) | DLP scope assessment document; risk acceptance if expanded DLP deferred | CLOSED 2026-07-31. Formalised as POL-019 (DLP Policy) — §3 documents current DLP coverage (Google Workspace email/Drive), §4 records a formal, CISO-accepted residual risk for the remaining coverage gap (tiered per POL-014 §5), §5 sets a phased roadmap (AWS Macie, CASB). Satisfies the verification method: a DLP scope assessment document with documented risk acceptance now exists.
CAP Summary: 8 actions total ¦ Open: 1 ¦ In Progress: 0 ¦ Closed: 7 ¦ Next Review: 2026-10-01

## 📈 Dashboard
CAP Progress Dashboard - ResolvX Internal Audit
Metric | Value | Target | Status
Total CAP Actions | 8 | — | —
Minor Nonconformities | 5 | 0 open at audit close | Conformant
Observations | 3 | All actioned | 2 of 3 Closed
Major Nonconformities | 0 | 0 | Conformant
Actions: Open | 1 | 0 overdue | On Track
Actions: In Progress | 0 | — | Conformant
Actions: Closed | 7 | All closed by Q3 2026 | On Track
High-Priority Actions Due < 30 days | 1 (F-007, due 2026-08-31) | All on track | On Track
Overdue Actions | 0 | 0 | Conformant
Next CAP Review Date | 2026-10-01 | Monthly | —