## 📋 Cover
ResolvX
Internal Audit Checklist
ISMS Audit - ISO 27001:2022 ¦ SOC 2 Trust Service Criteria ¦ NIST CSF 2.0
Document ID | AUDIT-CL-001
Version | 1.1
Audit Period | Q1 2026 (baseline) — Re-Audit Q3 2026
Audit Type | Internal ISMS Audit - Clause 9.2
Lead Auditor | GRC Lead - Derick G. Dmello
Scope | Full ISMS scope - all ResolvX systems, processes, and controls
Framework | ISO 27001:2022 Annex A - SOC 2 TSC CC1-CC9 - NIST CSF 2.0
Classification | Internal - Confidential
Finding Classification Key
Conformant | Control is implemented and effective - evidence reviewed and satisfactory
Minor NC | Minor nonconformity - control exists but has a gap; does not immediately threaten ISMS objectives
Major NC | Major nonconformity - control missing or critically failed; directly threatens ISMS objectives or audit certification
Observation | Opportunity for improvement - not a nonconformity but worth strengthening
Not Tested | Out of scope for this audit cycle or evidence request pending

## 📊 ISO 27001 Audit
ISO 27001:2022 - Internal Audit Checklist ¦ Audit Period: Q1 2026 (baseline) — Re-Audit Q2 2026
# | Control Ref | Control Name | Audit Question / Test Procedure | Evidence Reviewed | Test Result | Auditor Notes | Finding
Organisational Controls
1 | A5.1 | IS Policies | Is an approved IS Policy suite in place covering all required domains? Are policies reviewed annually? | POL-001 to POL-026 reviewed; approval signatures verified; version dates confirmed | All policies in place, approved by CISO, dated Jan 2026 | All policies reviewed and approved. | Conformant
2 | A5.2 | IS Roles and Responsibilities | Are information security roles and responsibilities defined, documented, and communicated? | Controls Owners Register reviewed; job descriptions checked for GRC Lead and CISO roles | Controls Owners Register (Phase 3) maps all Annex A controls to named owners | Controls Owners Register complete. GRC Lead and CISO roles have documented responsibilities. | Conformant
3 | A5.9 | Inventory of Information Assets | Is a complete and current inventory of information assets maintained? | Company profile asset inventory (Phase 1) reviewed | Asset register formalised as POL-011 (Asset Management Policy) — document ID, version control, GRC Lead ownership, annual review cycle | Formal ISMS document now exists (POL-011), closing the original observation. [Re-audit 2026-07-31] | Conformant
4 | A5.12 | Classification of Information | Is information classified according to a documented scheme? Is classification applied in practice? | POL-004 reviewed; sample of documents checked for classification labels | Classification label templates added to Workspace; workflow reminder configured; document owners re-trained | Re-test of the original 10-document sample confirms all documents correctly labelled. Nonconformity closed. [Re-audit 2026-07-31] | Conformant
5 | A5.15 | Access Control | Are access control rules documented and enforced? Is RBAC applied? Are reviews conducted? | POL-003 reviewed; Okta RBAC config reviewed; Q4 2025 access review records checked | POL-003 in place; Okta groups map to roles; Q4 2025 access review completed | Access control policy implemented. Quarterly access review conducted Dec 2025. Evidence available. | Conformant
6 | A5.16 | Identity Management | Is the full identity lifecycle (provisioning, changes, deprovisioning) managed and documented? | JML process documentation reviewed; sample of 5 leavers checked in Okta | JML process in POL-003; Okta deprovisioning checked for 5 recent leavers | 3/5 leavers deprovisioned same day; 2 deprovisioned within 3 days - within 48-hour SLA. No overdue accounts found. | Conformant
7 | A5.17 | Authentication Information | Are password and MFA policies documented and enforced? Are shared credentials prohibited? | MFA enforcement in Okta reviewed; 1Password business usage reviewed | FIDO2 hardware keys deployed for all 8 admin accounts; Okta admin group policy enforces hardware key authentication | Hardware key enforcement now in place, validated via Okta admin console. Nonconformity closed. [Re-audit 2026-07-31] | Conformant
8 | A5.19 | IS in Supplier Relationships | Are IS requirements defined for suppliers? Are DPAs and security clauses in all contracts? | POL-005 reviewed; sample of 3 vendor contracts reviewed for security clauses | POL-005 in place; vendor register shows DPA status; Tier 1 assessments completed | Vendor management framework complete. DPAs in place for all data-processing vendors. Tier 1 assessments filed. | Conformant
9 | A5.23 | IS for Cloud Services | Are cloud services managed with defined security requirements? Is shadow IT prohibited? | POL-005 Section 4 reviewed; AWS configuration reviewed; Okta SSO coverage checked | SSO coverage: 14/14 vendors — both legacy integrations migrated to Okta SSO (SAML/OIDC) | Full SSO coverage achieved; vendor register updated per POL-005. Nonconformity closed. [Re-audit 2026-07-31] | Conformant
10 | A5.24 | IR Planning and Preparation | Is an incident response plan documented, approved, and tested? | IR-PLAN-001 reviewed; tabletop exercise report reviewed | IR-PLAN-001 v1.0 approved; tabletop exercise conducted Feb 2026 | IR plan complete and tested. Tabletop exercise report documents 3 medium findings - all remediated. | Conformant
11 | A5.25 | Assessment of IS Events | Is there a process to assess security events and determine if they are incidents? Is a log maintained? | Incident Log Template reviewed; IRT escalation criteria in IR-PLAN-001 reviewed | Severity model (P1-P4) documented in IR-PLAN-001; incident log template ready | Event assessment criteria documented and tested. Incident log in use. | Conformant
12 | A5.26 | Response to IS Incidents | Are there documented response procedures for key incident types? Have they been tested? | Runbooks IR-RB-001/002/003 reviewed; tabletop results reviewed | 3 runbooks in place covering phishing, ransomware, data breach | Runbooks complete and aligned to IR-PLAN-001. Tested via tabletop Feb 2026. | Conformant
13 | A5.27 | Learning from IS Incidents | Is there a lessons learned process? Are incidents driving ISMS improvements? | Tabletop report reviewed; action items log reviewed | Post-exercise action items documented; 3 runbook updates made | Lessons learned process embedded in IR-PLAN-001 Section 4.4. Evidence of improvement from Feb 2026 exercise. | Conformant
14 | A5.28 | Collection of Evidence | Are evidence handling procedures defined? Is chain of custody maintained? | IR-PLAN-001 Section 5 reviewed | Evidence handling procedures documented in IR Plan §7; Evidence/Chain-of-Custody Log template now built (IR Plan Appendix B) | Template now exists but still not exercised in a live P1/P2 incident or dedicated tabletop. Observation remains open — tracked as CAP F-007. [Re-audit 2026-07-31] | Observation
15 | A5.34 | Privacy and Protection of PII | Is a privacy policy in place? Is a ROPA maintained? Is there a DSR process? | POL-006 reviewed; ROPA reviewed; DSR process reviewed | POL-006 Part A (policy), Part B (ROPA), Part C (DSR process) all complete | Privacy programme complete. ROPA covers 6 controller activities and 3 processor activities. DSR process documented. | Conformant
People Controls
16 | A6.1 | Screening | Are background checks conducted for all employees and contractors prior to access? | HR policy reviewed; sample of 3 recent hire records checked | Background check requirement in employee handbook; 3/3 sample had completed checks | Background check process in place. Evidence available for sampled hires. | Conformant
17 | A6.3 | IS Awareness / Education / Training | Do all staff complete security awareness training? Is phishing simulation conducted? | Training completion records reviewed; phishing simulation results reviewed | Annual security awareness training: 120/120 employees complete (100%) | All 8 previously-overdue employees completed training; automated LMS escalation configured per POL-023 §5 for future cycles. Nonconformity closed. [Re-audit 2026-07-31] | Conformant
18 | A6.5 | Responsibilities After Termination | Are access rights revoked promptly on termination? Are NDAs enforced post-employment? | Okta deprovisioning records reviewed; NDA templates reviewed | Okta account deprovisioning: 48-hour SLA; 3 of 5 leavers same-day | Process in place. 48-hour SLA met for all reviewed leavers. NDAs signed at onboarding. | Conformant
19 | A6.7 | Remote Working | Are remote working security requirements documented and enforced? Are endpoints managed? | POL-002 Section 3 reviewed; Jamf enrollment records reviewed | Remote working policy in POL-002; Jamf MDM coverage checked | Remote working policy in place. Jamf coverage: 118/120 endpoints enrolled (2 pending - new starters). Acceptable. | Conformant
Physical Controls
20 | A7.1 | Physical Security Perimeters | Are physical security measures in place for offices and data facilities? ResolvX is cloud-native - verify AWS physical security via SOC 2. | AWS SOC 2 Type II report reviewed for physical security sections | AWS SOC 2 confirms physical access controls at data centre level | ResolvX is cloud-native with no owned data centres. AWS physical controls verified via SOC 2 Type II. Office physical security: badge access in place. | Conformant
21 | A7.8 | Equipment Siting and Protection | Is equipment protected against theft and environmental threats? Are screen locks enforced? | Jamf configuration profiles reviewed; clean desk policy checked | Jamf enforces 5-minute screen lock; full-disk encryption on all endpoints | Endpoint encryption and screen lock enforced via Jamf. Clean desk policy in place. | Conformant
Technology Controls
22 | A8.2 | Privileged Access Rights | Are privileged accounts managed with enhanced controls? Is PAM in place? | AWS IAM privileged account config reviewed; 1Password admin vault reviewed | FIDO2 hardware key enforced for AWS console admin access via Okta; break-glass credential handling formalised (POL-012 §5) | Nonconformity closed — see A5.17. [Re-audit 2026-07-31] | Conformant
23 | A8.5 | Secure Authentication | Is MFA enforced for all systems and remote access? Are weak authentication methods prohibited? | Okta MFA policies reviewed; AWS console MFA checked | MFA: 100% enforced via Okta for all SaaS; AWS console MFA enforced | MFA enforced across all systems. No password-only access identified. | Conformant
24 | A8.7 | Protection Against Malware | Are malware protection controls in place across endpoints and cloud workloads? | Jamf endpoint security config reviewed; AWS GuardDuty reviewed; Snyk reviewed | Jamf + EDR on all endpoints; GuardDuty enabled in all AWS regions; Snyk CI/CD integration | Anti-malware controls in place across endpoint and cloud layers. Snyk integrated in CI/CD pipeline. | Conformant
25 | A8.8 | Management of Technical Vulnerabilities | Is there a documented vulnerability management process? Are patch SLAs defined and met? | Snyk reports reviewed; patch SLAs in POL-001 reviewed; recent vuln report reviewed | Snyk report confirms 0 open High-severity findings >30 days; POL-010 formalises 30-day SLA with automatic Jira ticket creation | Both findings remediated within sprint. Systemic fix (auto-ticketing, POL-010 §6.1) now in place, addressing root cause. Nonconformity closed. [Re-audit 2026-07-31] | Conformant
26 | A8.9 | Configuration Management | Are baseline configurations documented and enforced? Is IaC scanning in place? | Jamf configuration profiles reviewed; Snyk IaC scanning reviewed | Jamf baseline profiles for macOS; Snyk IaC scanning in GitHub Actions pipeline | Configuration management in place for endpoints and IaC. Baseline documentation adequate. | Conformant
27 | A8.12 | Data Leakage Prevention | Are DLP controls in place to prevent unauthorised exfiltration of sensitive data? | Google Workspace DLP rules reviewed; Okta CASB config reviewed | POL-019 (DLP Policy) formally documents current scope (Workspace email/Drive) and a phased roadmap (AWS Macie, CASB) | Residual coverage gap (API/S3/endpoint) now formally accepted by CISO per POL-014 §5 tiered authority, rather than left undocumented. Observation remains open by design — a formal risk acceptance, not a closed gap. [Re-audit 2026-07-31] | Observation
28 | A8.15 | Logging | Are audit logs captured across all critical systems? Are logs retained per policy? | AWS CloudTrail config reviewed; Okta audit log retention checked; Datadog reviewed | CloudTrail: all regions enabled, 12-month retention in S3. Okta: 12-month retention. Datadog: 90-day retention. | Logging in place across all critical systems. Log integrity: CloudTrail with S3 validation enabled. | Conformant
29 | A8.16 | Monitoring Activities | Is continuous monitoring in place? Are alerts reviewed and actioned? | Datadog alerts config reviewed; GuardDuty findings reviewed; Okta alerts reviewed | Datadog: alerting on anomalies; GuardDuty: findings reviewed weekly by Head of Cloud Ops | Monitoring stack in place. Alert review cadence documented. No unreviewed critical alerts found in period. | Conformant
30 | A8.24 | Use of Cryptography | Is a cryptography policy in place? Is encryption applied at rest and in transit per policy? | POL-001 Section 6 reviewed; AWS KMS config reviewed; TLS configuration checked | AWS: AES-256 at rest; TLS 1.3 in transit; KMS for key management | Cryptography policy in place and implemented. All production data encrypted at rest and in transit. | Conformant
31 | A8.28 | Secure Coding | Are secure coding standards in place? Is SAST/SCA conducted? Are findings tracked? | Snyk SAST/SCA reports reviewed; GitHub branch protection rules reviewed | Snyk: SAST and SCA in all repos; branch protection: PRs required; code review mandatory | Secure coding practices in place. Snyk integrated. 2 open High findings tracked to owners. | Conformant
Summary: 31 controls tested ¦ Conformant: 22 ¦ Minor NC: 6 ¦ Major NC: 0 ¦ Observations: 3

## 📊 SOC 2 TSC Audit
SOC 2 Trust Service Criteria - Audit Checklist ¦ Audit Period: Q1 2026 (baseline) — Re-Audit Q2 2026
# | Control Ref | Control Name | Audit Question / Test Procedure | Evidence Reviewed | Test Result | Auditor Notes | Finding
Control Environment
1 | CC1.1 | COSO Principle 1 | Does ResolvX demonstrate commitment to integrity and ethical values through documented policies and leadership tone? | POL-001 through POL-026 reviewed; acceptable use policy; code of conduct | 26 policies in place; AUP (POL-002) addresses ethical use | Policies establish ethical framework. Leadership commitment evidenced by CISO approval of all policies. | Conformant
2 | CC1.3 | Organisational Structure | Are reporting lines, roles, and accountabilities for information security clearly defined? | Controls Owners Register reviewed; org chart reviewed | Controls Owners Register maps all Annex A controls to named owners with titles | Organisational structure for IS documented. GRC Lead, CISO, and technical owners named. | Conformant
Communication and Information
3 | CC2.1 | Information Quality | Does ResolvX obtain and use relevant, quality information to support the functioning of internal controls? | Risk register reviewed; gap analysis reviewed; monitoring data reviewed | Risk register, gap analysis, and control matrices maintained | Information quality inputs to control framework are in place and current. | Conformant
4 | CC2.2 | Internal Communication | Are information security requirements communicated internally to relevant personnel? | Policy distribution records reviewed; awareness training records reviewed | Training completion now 100% (120/120); automated overdue-training escalation configured per POL-023 §5 | Nonconformity closed — see A6.3. [Re-audit 2026-07-31] | Conformant
Logical and Physical Access
5 | CC6.1 | Logical Access Security | Are logical access controls in place to prevent unauthorised access? | POL-003 reviewed; Okta RBAC configuration reviewed; MFA enforcement verified | POL-003; Okta RBAC; MFA 100% enforced; quarterly access reviews | Comprehensive logical access controls in place. RBAC, MFA, and quarterly reviews all evidenced. | Conformant
6 | CC6.2 | New Account Provisioning | Is new user access provisioned using formal request and approval processes? | Okta provisioning workflow reviewed; sample of 5 new users traced from HR to access grant | Okta SCIM provisioning from HRIS; manager approval required for elevated access | Provisioning process formal and documented. Sampled 5 new users - all correctly provisioned. | Conformant
7 | CC6.3 | Access Removal | Is access removed promptly when users change roles or leave? | Okta deprovisioning records reviewed; JML process in POL-003 | 48-hour deprovisioning SLA; 5 leavers reviewed | Access removal process in place. All sampled leavers deprovisioned within SLA. | Conformant
8 | CC6.6 | Logical Access Security - External Users | Are controls in place to restrict access from external sources (internet)? | AWS security group configurations reviewed; VPN policy reviewed; API gateway reviewed | No direct public access to production databases; API gateway with auth required | External access restricted via security groups and API gateway. No unauthorised public exposure found. | Conformant
9 | CC6.7 | Transmission Integrity | Is data in transit protected against unauthorised disclosure or modification? | TLS configuration reviewed; API endpoint encryption checked | TLS 1.3 enforced on all public endpoints; internal service communication encrypted | Data in transit encrypted. TLS 1.3 confirmed on all public endpoints. | Conformant
10 | CC6.8 | Malware Protection | Are controls in place to detect, prevent, and mitigate malware? | Jamf endpoint security reviewed; GuardDuty reviewed; Snyk reviewed | Endpoint EDR; GuardDuty; Snyk SAST/SCA | Multi-layer malware protection in place across endpoints, cloud, and CI/CD. | Conformant
System Operations
11 | CC7.1 | Vulnerability Management | Are vulnerabilities detected, analysed, and remediated in a timely manner? | Snyk reports reviewed; patch SLA compliance reviewed | Snyk report confirms 0 open High-severity findings >30 days; POL-010 SLA and auto-ticketing now formalised | Nonconformity closed — see A8.8. [Re-audit 2026-07-31] | Conformant
12 | CC7.2 | Monitoring | Is the system continuously monitored for anomalies and security events? | Datadog alert configuration reviewed; GuardDuty findings reviewed | Datadog + GuardDuty + Okta monitoring active; weekly review cadence | Continuous monitoring in place. Alert review process documented and evidenced. | Conformant
13 | CC7.3 | Incident Evaluation | Are security incidents detected and classified using defined criteria? | IR-PLAN-001 severity model reviewed; incident log reviewed | P1-P4 severity model; incident log template in use | Incident evaluation criteria defined and tested. Tabletop exercise validated classification process. | Conformant
14 | CC7.4 | Incident Response | Are incidents responded to according to documented procedures? | IR-PLAN-001 and runbooks reviewed; tabletop report reviewed | IR plan + 3 runbooks; tested Feb 2026 | Incident response procedures comprehensive and tested. | Conformant
15 | CC7.5 | Incident Recovery | Are recovery procedures in place and tested? | IR-PLAN-001 RTO targets reviewed; backup restoration test records reviewed | RTO targets defined; backup restoration tested quarterly | Recovery procedures documented. Backup restoration tested Q1 2026. | Conformant
Risk Mitigation - Vendor
16 | CC9.1 | Vendor Risk Management | Does ResolvX assess and manage risks associated with third-party vendors? | POL-005 reviewed; vendor register reviewed; Tier 1 assessments reviewed | 14 vendors registered; 6 Tier 1 assessments completed; DPAs in place | Comprehensive vendor risk management programme in place. All Tier 1 vendors assessed. | Conformant
17 | CC9.2 | Vendor Monitoring | Are vendor security practices monitored on an ongoing basis? | Vendor register review schedule reviewed; vendor notification procedures reviewed | Annual review cycle for Tier 1/2; 72-hour incident notification in all DPAs | Vendor monitoring process defined. Next scheduled review: Q2 2026 for Tier 1 vendors. | Conformant
Summary: 17 TSC criteria tested ¦ Conformant: 15 ¦ Minor NC: 2 ¦ Major NC: 0 ¦ Observations: 0