## 🏠 Executive Dashboard
ResolvX — ISMS Compliance Dashboard — Q2 2026 (Updated)
DASH-001 ¦ v1.1 ¦ Owner: GRC Lead ¦ Classification: Internal - Restricted ¦ Reporting Period: Q2 2026 (baseline: Q1 2026)
PROGRAMME STATUS
Phase 1 Foundation |  | Phase 2 Risk & Controls |  | Phase 3 Policies & Vendors |  | Phase 4 Incident Response | Phase 5 Audit Readiness | Phase 6 Trust Center
✓ Complete |  | ✓ Complete |  | ✓ Complete |  | ✓ Complete | ✓ Complete | ⬤ Active
KEY METRICS — Q3 2026
ISO 27001 Controls Implemented |  | SOC 2 TSC Criteria Ready |  | Major Nonconformities |  | Vendor Risk Tier 1 Assessed | CAP Actions Open | SOC 2 Type II Readiness
77/93 |  | 17/17 |  | 0 |  | 6/6 | 1 | 98%
83% — up from 16% baseline |  | 100% — up from 88% |  | Re-Audit Q2 2026 |  | All Low Risk | F-007 only — was 6 | FULLY READY
CONTROL COVERAGE BY DOMAIN — ISO 27001:2022 Annex A (full 93-control scope)
Domain |  |  | Implemented |  | Partial |  | Planned
Organisational |  |  | 28 |  | 8 |  | 1
People |  |  | 8 |  | 0 |  | 0
Physical |  |  | 13 |  | 1 |  | 0
Technological |  |  | 28 |  | 5 |  | 1
SOC 2 TYPE II READINESS BY STATUS
Status | Count
Fully Ready | 17
Partially Ready | 0
Not Ready | 0

## 📊 Risk Overview
Risk Register Summary — ResolvX ISMS — Q2 2026
Source: risk_register.xlsx v1.1 ¦ Owner: GRC Lead ¦ Next Review: 2026-10-01
KEY METRICS
Total Risks Registered |  | High / Critical Residual |  | Moderate Residual |  | Risks Fully Mitigated
25 |  | 0 |  | 7 |  | 10
All domains |  | Down from 3 |  | Down from 12 |  | Up from 0
TOP RESIDUAL RISKS (Moderate tier — highest remaining)
Risk | Category | Residual Level | Residual Score | Treatment | Owner
Ransomware attack | Cyber Threat | Moderate | 8 | Mitigate: immutable backups, MFA-delete (POL-009) | Head of Cloud Ops
API vulnerability exploitation | Cyber Threat | Moderate | 8 | Mitigate: 30-day SLA, continuous scanning (POL-010) | DevSecOps Engineer
Software supply chain attack | Cyber Threat | Moderate | 8 | Mitigate: SCA/SAST in CI/CD (POL-018) | DevSecOps Engineer
AWS S3 misconfiguration | Cloud & Infrastructure | Moderate | 8 | Mitigate: CIS baseline, public S3 disabled (POL-022) | Head of Cloud Ops
IAM over-privilege | Cloud & Infrastructure | Moderate | 8 | Mitigate: least-privilege baseline (POL-022) | Head of Cloud Ops
AWS vendor concentration | Vendor & Third-Party | Moderate | 8 | Documented shared-responsibility; multi-cloud eval pending | GRC Lead
Stripe integration breach (PCI) | Vendor & Third-Party | Moderate | 8 | Deferred by design — Step 3 PCI-DSS material | GRC Lead
RESIDUAL RISK LEVEL DISTRIBUTION
Level | Count
Moderate | 7
Low | 8
Very Low | 10

## 📊 Vendor Risk
Vendor Risk Overview — ResolvX TPRM — Q2 2026
Source: Vendor Register + Tier 1 Assessments (POL-005) ¦ 14 vendors ¦ No changes this cycle — confirmed 2026-07-31
KEY METRICS (unchanged since Q1 2026 — folder reviewed, no update needed)
Total Vendors Registered |  | Tier 1 Critical Vendors Assessed |  | DPAs Executed |  | SOC 2/ISO 27001 Coverage T1+T2
14 |  | 6/6 |  | 13/14 |  | 12/12
4 tiers |  | All Low Risk |  | All data processors |  | 100%
TIER 1 VENDOR ASSESSMENT SUMMARY
Vendor | Category | Tier | Score | Residual Risk | DPA | Next Review
AWS | Cloud Infrastructure | Tier 1 | 94/100 | Low | Active | 2027-01
Okta | Identity / SSO | Tier 1 | 90/100 | Low | Active | 2026-05
GitHub | Source Code Mgmt | Tier 1 | 96/100 | Low | Active | 2026-08
Google Workspace | Collaboration | Tier 1 | 95/100 | Low | Active | 2026-12
Jamf | Endpoint MDM | Tier 1 | 86/100 | Low | Active | 2026-02
1Password | Credential Mgmt | Tier 1 | 92/100 | Low | Active | 2026-04
Slack | Messaging | Tier 2 | — | Low | Active | 2026-Q3
Datadog | Monitoring | Tier 2 | — | Low | Active | 2026-Q3
Rippling | HRIS / Payroll | Tier 2 | — | Medium | Active | 2026-Q3
Stripe | Payments | Tier 2 | — | Low | Active | 2026-Q3

## 📊 CAP Tracker
Corrective Action Plan Tracker — Source: Re-Audit Q2 2026
AUDIT-CAP-001 v1.1 ¦ 8 total actions ¦ Monthly review ¦ Owner: GRC Lead
KEY METRICS
Total CAP Actions |  | Open |  | In Progress |  | Closed
8 |  | 1 |  | 0 |  | 7
All domains |  | F-007 only |  | Down from 2 |  | Up from 0
CORRECTIVE ACTION REGISTER
ID | Source | Action Summary | Owner | Due Date | Priority | Status
F-001 | NC-001 A5.12 | Classification labels added to templates; owners retrained; re-tested | GRC Lead | 2026-07-31 | Medium | Closed
F-002 | NC-002 A5.17 | FIDO2 keys procured for all 8 admin accounts; Okta enforcement verified | IT Admin | 2026-07-31 | Medium | Closed
F-003 | NC-003 A5.23 | Both legacy SaaS tools migrated to Okta SSO; register updated | IT Admin + DevSecOps | 2026-07-31 | Medium | Closed
F-004 | NC-004 A6.3 | All 8 overdue employees completed training; LMS auto-escalation configured | GRC Lead + HR | 2026-07-31 | Medium | Closed
F-005 | NC-005 A8.8 | Both High Snyk findings remediated; Snyk-Jira auto-ticketing configured | DevSecOps | 2026-07-31 | High | Closed
F-006 | OBS-001 A5.9 | Formalised as POL-011 — document ID, version control, review cycle | GRC Lead | 2026-07-31 | Low | Closed
F-007 | OBS-002 A5.28 | Chain-of-custody template built (IR Plan Appx B); not yet exercised live | GRC Lead | 2026-08-31 | Low | Open
F-008 | OBS-003 A8.12 | POL-019 documents scope + roadmap; residual risk formally accepted (POL-014 §5) | GRC Lead + Cloud Ops | 2026-07-31 | Low | Closed (Risk Accepted)

## 📅 Programme Timeline
ResolvX GRC Programme Timeline — 2026-2027 Roadmap
Full programme: Q4 2025 - Q1 2027 ¦ SOC 2 Type II target: Mar 2027 ¦ Updated: 2026-07-31
Milestone | Start | End / Target | Key Deliverables | Status
Phase 1: Programme Foundation | Q4 2025 | Q4 2025 | Company profile, risk methodology, gap analysis, programme charter | Complete
Phase 2: Risk and Controls | Q4 2025 | 2026-07-31 | 25-risk register, control matrices, gap analysis — fully reconciled against POL-007-026 | Complete
Phase 3: Policies and Vendor Risk | Q4 2025 | 2026-07-31 | 26 policies (POL-001-026), vendor register, VSQ appendix, Tier 1 assessments | Complete
Phase 4: Incident Response | Q1 2026 | 2026-07-31 | IR plan (v1.1), 3 runbooks, tabletop exercise, 2 new appendices (Post-Incident Report, Chain-of-Custody) | Complete
Phase 5: Audit Readiness | Q1 2026 | 2026-07-31 | Internal audit re-run (7/8 CAP closed), SOC 2 readiness (FULLY READY), CAP reconciled | Complete
Phase 6: Dashboard + Trust Center | Q1 2026 | Q4 2026 | Compliance dashboard (this document), programme foundation refresh, public trust center page | Active
CAP Remediation | Q2 2026 | 2026-07-31 | All 8 CAP actions addressed — 7 closed, F-007 tracked for a dedicated evidence-handling exercise | Complete
External Audit Firm Selection | 2026-08 | 2026-Q4 | Select SOC 2 audit firm; pre-audit walkthrough; agree observation period start | Planned
SOC 2 Observation Period | 2026-Q4 | 2027-Q2 | 6-month evidence collection period; monthly GRC checkpoints | Planned
SOC 2 Audit Fieldwork | 2027-Q2 | 2027-Q2 | Auditor testing and interviews; evidence response | Planned
SOC 2 Type II Report | 2027-Q3 | 2027-Q3 | Report issued; distribute to clients under NDA | Planned