## 📋 Tabletop Report
ResolvX - Tabletop Exercise Report
Exercise: Operation Locked Gate ¦ Scenario: Ransomware Attack on Production ¦ Date: 2026-02-14
Exercise Metadata
Exercise Title | Operation Locked Gate
Exercise Type | Tabletop Discussion Exercise
Date Conducted | 2026-02-14
Duration | 3 hours (09:00 - 12:00)
Facilitator | GRC Lead - Derick G. Dmello
Observer | CISO
Scenario | Ransomware infection originating from phishing email; lateral movement to AWS; exfiltration before encryption
Frameworks Tested | NIST SP 800-61 Rev 2 lifecycle; ISO A5.24-A5.28; SOC 2 CC7.3-CC7.5
IR Plan Version Tested | IR-PLAN-001 v1.0
Participants
Name / Role | Function in Exercise | Attended?
GRC Lead - Derick G. Dmello | Incident Commander / Facilitator | Yes
CISO | Executive decision-maker / Observer | Yes
Head of Cloud Ops | Technical Lead - AWS response | Yes
IT Admin | Identity and endpoint response | Yes
DevSecOps Engineer | Malware analysis / code integrity | Yes
Legal Counsel (external) | Regulatory notification decisions | Yes
VP Engineering | Recovery prioritisation | Yes
Head of HR | Personnel and awareness actions | Yes
Scenario Injects and Team Responses
Inject / Event | Team Response Recorded | Expected Response | Gap Identified?
T+0: Datadog alert fires - unusual S3 write activity; GuardDuty flags EC2 instance beaconing to known C2 IP | Head of Cloud Ops identified alert within 2 minutes. Notified GRC Lead via Slack. Incident log opened. | Detect within 15 min; open incident log; notify GRC Lead immediately | No
T+15 min: Engineer reports files on shared drive showing .locked extension; ransom note found on desktop | GRC Lead declared P1 immediately. Signal group activated. IT Admin began Jamf isolation of affected endpoint. | Declare P1; activate IRT via out-of-band channel; isolate affected endpoint immediately | No
T+20 min: Head of Cloud Ops identifies 3 EC2 instances with anomalous outbound traffic; suspects lateral movement | Security group rules modified to isolate instances. Team debated whether to terminate instances - correctly decided to isolate and preserve for forensics. | Isolate in-place; do not terminate; take EBS snapshots before any further action | Minor - initial instinct was to terminate. Runbook guidance needed reinforcement.
T+45 min: VPC flow logs show 4.2 GB of outbound data transfer to external IP 2 hours before encryption began | Team correctly identified this as potential double-extortion. GRC Lead started GDPR 72-hour clock. Legal engaged. | Treat exfiltration as data breach; start GDPR clock; engage Legal; notify CISO | No
T+1 hr: CISO asks: should we pay the ransom? Backups are confirmed intact but recovery will take 8 hours. | Team consensus: do not pay. Backups intact. Legal confirmed no sanctions obligation risk if payment refused. Recovery plan activated. | Do not pay if clean backups exist; Legal to assess sanctions risk; recovery from backup is the preferred path | No
T+2 hr: Legal asks: do we need to notify the Irish DPC? Client data was on affected systems. | GRC Lead and Legal correctly identified GDPR Art. 33 obligation. Team drafted notification outline using pre-prepared template. Acknowledged 72-hour deadline. | Yes - notify DPC within 72 hours. Also notify affected client(s) per DPA obligations. | Minor - team initially confused about whether exfiltration (not just encryption) triggers notification. Clarified in debrief.
T+2.5 hr: IT Admin asks: should we reset all passwords company-wide or just affected accounts? | Team debated. Facilitator guided to correct answer: P1 ransomware event = rotate all credentials organisation-wide, not just affected accounts. | Org-wide credential rotation for P1 ransomware; assume all credentials are compromised | Yes - team initially proposed scoped rotation only. This is a gap to address in next awareness session.
T+3 hr: Team asked to plan recovery sequence - what comes back first? | VP Engineering led recovery prioritisation: (1) authentication systems (Okta), (2) core dispute processing service, (3) internal tools. Sequence was logical. | Prioritise authentication; then critical client-facing services; then internal tools | No
Findings and Observations
Finding | Detail | Severity | Status
F-001: Terminate vs. isolate confusion | Team's initial instinct was to terminate compromised EC2 instances rather than isolate them. Termination would destroy forensic evidence and prevent EBS snapshot capture. Runbook IR-RB-002 guidance needs reinforcement in pre-exercise briefing. | Medium | Runbook updated; to be covered in next awareness session
F-002: GDPR exfiltration notification ambiguity | Team was initially uncertain whether exfiltration (without confirmed decryption) triggers GDPR Art. 33 notification. Clarified: exfiltration of personal data is a breach regardless of encryption. Pre-drafted notification templates were used effectively once decision was made. | Medium | IR-RB-003 updated with explicit clarification; Legal to run 30-min GDPR breach refresher
F-003: Credential rotation scope | Team proposed scoped credential rotation (affected accounts only) for a P1 ransomware event. Correct approach is org-wide rotation. Gap reflects lack of clarity in IR-PLAN-001 Section 4.3.3. Plan updated. | Medium | IR-PLAN-001 Section 4.3.3 updated; added to onboarding checklist
F-004: Out-of-band comms worked well | Signal group for IRT was activated promptly and used effectively throughout. No sensitive information was shared on corporate Slack during the exercise. Positive finding. | Positive | No action required
F-005: Backup readiness confirmed | Head of Cloud Ops was able to confirm backup integrity and estimated RTO within 45 minutes of the exercise start. AWS backup procedures are well-understood by technical team. | Positive | No action required
F-006: Legal response time | External Legal counsel joined the exercise 12 minutes after being paged. For a real P1 incident, 12 minutes is acceptable but should be targeted to improve to 5 minutes via a standing on-call arrangement. | Low | Legal on-call arrangement to be formalised in retainer contract by Q2 2026
Action Items
Action | Owner | Due Date | Status
Update IR-RB-002 to explicitly prohibit terminating isolated instances before EBS snapshot | GRC Lead | 2026-02-21 | Complete
Update IR-RB-003 to clarify exfiltration triggers GDPR notification regardless of encryption | GRC Lead | 2026-02-21 | Complete
Update IR-PLAN-001 Section 4.3.3 to specify org-wide credential rotation for P1 ransomware | GRC Lead | 2026-02-21 | Complete
Add Legal on-call 5-minute SLA to retainer contract | Legal / GRC Lead | 2026-03-31 | In Progress
Run 30-minute GDPR breach notification refresher for all IRT members | GRC Lead + Legal | 2026-03-15 | Planned
Include credential rotation scope in annual security awareness training | GRC Lead | 2026-04-01 | Planned
Schedule next tabletop exercise - scenario: data breach via vendor | GRC Lead | 2026-08-01 | Planned
Overall Assessment
Overall Rating | SATISFACTORY - IRT demonstrated sound foundational IR capability with 3 medium findings. No critical gaps identified.
IR Plan Fitness | IR-PLAN-001 v1.0 is fit for purpose. Three updates made following this exercise (see action items). Next review: Q1 2027 or after next P1/P2 incident.
Next Exercise | Tabletop Exercise 2 - Scenario: Data Breach via Vendor (target: 2026-08). Functional phishing drill: 2026-06.